## Sheet1
Task Number | Planned Action | Planned Outcome | Time Estimated | Target Completion Date | Criterion
1 | Research and identify a suitable client who has a genuine software need | Approach almost a dozen known people amongst family and friends. Found a potential client (Ms. Gloria Benny) who is founder of an NGO | 2 Weeks | 2023-03-31 | Planning
2 | Preparatory discussion with Client | Set expectations with Client over a call for a formal Interview to follow and schedule a zoom meeting. | 10 minutes | 2023-04-01 | Planning
3 | Client Interview - 1 | Gloria detailed the organization functioning, current processes and the software requirements for me to consider. Date set for a follow-up interview. | 20 minutes | 2023-04-03 | Planning
4 | Requirement Refinement | Based on first interview, refined and transformed the client requirements into functional features, and listed them for client to review and approve. Researched on technology that can be used. | 1 Week | 2023-04-12 | Planning
5 | Client Interview - 2 | Discussed the features with the client and got approval after incorporating feedback. Technology stack was also agreed upon | 30 minutes | 2023-04-15 | Planning
6 | Learn RDBMS & SQL concepts | Learnt about Relational Database Management Systems (Oracle Database) and Strucutred Query Language (SQL). Familiarized with Entity Relationship Diagrams (ERDs) | 4 Weeks | 2023-06-24 | Design, Coding
7 | Database Modeling | Modeled the different entities of the client's organization which are within the scope of the project | 3 Weeks | 2023-07-15 | Design
8 | Client Review of Database Model | Showed the database design to client, sought feedback, made changes and obtained approval | 1 Week | 2023-07-22 | Design
9 | Learn Python & Flask to develop user interface | Learnt basics of Python programming language, web development, and Flask micro web framework | 3 Weeks | 2023-08-12 | Design, Coding
10 | User Interface Design | Designed the various user interface screens to be part of the project and their functional flows | 2 Weeks | 2023-08-26 | Design
11 | Client Review of User Interfaces | Sent the user interface designs for client review, sought feedback, made changes, and obtained approval for the design | 1 Week | 2023-09-09 | Design
12 | Cloud Account Creation | Created an Oracle Cloud Account for the project that provides free access to Oracle database | 1 Day | 2023-09-10 | Design, Coding
13 | Cloud Account Setup | Setup an instance of the Oracle database on the cloud acount and started it.Made initial configuration changes for the account. Downloaded the wallet to access the database. | 1 Day | 2023-09-12 | Design, Coding
14 | Database Tables Creation | Created all the database tables from approved datamodel along with relevant database indexes | 1 Day | 2023-09-13 | Coding
15 | SQL Scripts for sample data creation | Developed SQL insert scripts for sample data for the tables | 3 Days | 2023-09-20 | Coding
16 | User Interface Coding - Login Screen |  | 1 Week
17 | User Interface Coding - Dashboard Layout |  | 2 Weeks